## 2026
CHANNEL | STAGE | TARGETING | OBJECTIVE | STATUS | Format | MESSAGE | CTA | STATIC COPY | Image Suggestion | LANDING PAGE URL | FILE REVIEW | DEVELOPED BY | SIZES/FORMAT | SPECS LINK | First Draft Deadline | MATERIAL DEADLINE | LIVE DATE | END DATE | PROGRESS / NOTES / Phase | APPROVED | DESPATCHED? | FILE LOCATION

## Sheet 2
CHANNEL | STAGE | TARGETING | OBJECTIVE | STATUS | Format | MESSAGE | CTA | STATIC COPY | Image Suggestion | LANDING PAGE URL | FILE REVIEW | DEVELOPED BY | SIZES/FORMAT | SPECS LINK | First Draft Deadline | MATERIAL DEADLINE | LIVE DATE | END DATE | PROGRESS / NOTES / Phase | APPROVED | DESPATCHED? | FILE LOCATION
2026-09-10

## Sem 1 2027
CHANNEL | STAGE | TARGETING | OBJECTIVE | STATUS | Format | MESSAGE | CTA | STATIC COPY | Image Suggestion | LANDING PAGE URL | FILE REVIEW | DEVELOPED BY | SIZES/FORMAT | SPECS LINK | First Draft Deadline | MATERIAL DEADLINE | LIVE DATE | END DATE | PROGRESS / NOTES / Phase | APPROVED | DESPATCHED? | FILE LOCATION
Phase 1 — Connect
Display
Display | Prospecting (Connect) | VE | Traffic | IN PROGRESS | HTML5 | How do I upskill for the job I actually want? | Explore courses | Gain in-demand TAFE qualifications with hands-on learning and industry connections. | Trades student in workshop | https://example.rmit.local/study/vocational | R1 | Vietnam | 160x600px | https://example.rmit.local/specs/display | 2026-09-01 | 2026-09-08 | 2026-09-12 | 2026-11-03 | Round 1 feedback in Frame.io — tighten headline on the skyscraper. |  |  | https://example.rmit.local/files/sem1-display
[11 empty] | R1 |  | 300x250px
[5 empty] | HTML5 | [5 empty] | R1 |  | 300x600px
[11 empty] | R1 |  | 728x90px
|  |  | Traffic | IN PROGRESS | [6 empty] | R2 |  | 320x50px
[11 empty] | R2 |  | 970x250px | [5 empty] | Static fallback × 6 to follow.
Display | Prospecting (Connect) | PG | Traffic | BRIEFED | Static banner | How do I elevate my career without pausing it? | Find your course | Gain specialist skills with flexible postgraduate study designed for working professionals. | Professional on campus at dusk | https://example.rmit.local/study/postgraduate |  | Cyclone | 300x250px, 300x600px, 728x90px |  | 2026-09-06 | 2026-09-13 | 2026-09-16 | 2026-11-03
Social
Facebook and Instagram | Prospecting (Connect) | SL | Awareness | NEEDS REVIEW | Video - 15s | Your next chapter starts at RMIT. | Learn more | Hands-on learning, industry partners and a campus in the heart of Melbourne. | Hero film cutdown | https://example.rmit.local/study | https://f.io/demo-social-15 | Vietnam | 1x1 ¦ 9x16 ¦ 4x5 |  | 2026-08-30 | 2026-09-05 | 2026-09-12 | 2026-10-19 | Waiting on caption approval from Comms.
Facebook and Instagram | Prospecting (Connect) | SL | Awareness | COMPLETED | Carousel | Five ways RMIT gets you job-ready. | See how | Industry placements, real briefs and mentors who work in the field. | 5-card carousel | https://example.rmit.local/study/job-ready | R3 | Cyclone | 1080x1080 × 5 |  | 2026-08-21 | 2026-08-28 | 2026-09-02 | 2026-10-19 |  | Approved JW 28/8 | Y | https://example.rmit.local/files/sem1-carousel
YouTube | Prospecting (Connect) | ALL | Awareness | YET TO BRIEF | Video - 6s | Bumper — brand line only. |  |  | Hero film bumper | https://example.rmit.local/study |  | Vietnam | 16x9 |  | 2026-09-10 | 2026-09-16 | 2026-09-19 | 2026-10-19
Phase 2 — Convert
Social
Facebook and Instagram | Remarketing (Convert) | UG NSL | Traffic, Applications | YET TO BRIEF | Static | Applications close soon — finish yours today. | Apply now | Still deciding? Talk to us about pathways, credit transfer and scholarships. | Student at open day desk | https://example.rmit.local/apply |  | Comms | 1x1 ¦ 9x16 |  | 2026-09-24 | 2026-10-01 | 2026-10-04 | 2026-11-18
The Age (HPTO) | Remarketing (Convert) | PG | Traffic | YET TO BRIEF | Static banner | Study while you work. | Explore postgrad | Evening and online options across business, design and engineering. |  | https://example.rmit.local/study/postgraduate |  | Cyclone | 970x250px, 300x250px |  | 2026-09-26 | 2026-10-03 | 2026-10-07 | 2026-11-18
Spotify | Remarketing (Convert) | SL | Awareness | YET TO BRIEF | Audio - 30s | Radio script — 30s. | [5 empty] | Existing content | 30s audio + 640x640 companion |  |  |  | 2026-10-07 | 2026-11-18 | Reuse Sem 2 script with updated dates.

## Open Day 2026
CHANNEL | STAGE | TARGETING | OBJECTIVE | STATUS | Format | MESSAGE | CTA | STATIC COPY | Image Suggestion | LANDING PAGE URL | FILE REVIEW | DEVELOPED BY | SIZES/FORMAT | SPECS LINK | First Draft Deadline | MATERIAL DEADLINE | LIVE DATE | END DATE | PROGRESS / NOTES / Phase | APPROVED | DESPATCHED? | FILE LOCATION
Open Day 2026
Registration drive
Facebook and Instagram | Prospecting (Connect) | SL | KPIs: Registration, Cost per Registration | COMPLETED | Static | Save the date — Open Day, 9 August. | Register | Tour campuses, meet lecturers and see where your course could take you. | Campus crowd shot | https://example.rmit.local/open-day | R2 | Cyclone | 1x1 ¦ 9x16 |  | 2026-08-05 | 2026-08-11 | 2026-08-15 | 2026-09-14 |  | Approved PN 5/8 | Y
ATAR Notes | Prospecting (Connect) | SL | KPIs: Registration | FILE DELIVERY | Static banner | Ask us anything at Open Day. | Register |  |  | https://example.rmit.local/open-day | R2 | Vietnam | 300x250px, 728x90px |  | 2026-08-25 | 2026-08-31 | 2026-09-03 | 2026-09-14 | Files sent to publisher; awaiting confirmation.
YouTube
Reminder
Facebook and Instagram | Remarketing (Convert) | SL | Attendance | BRIEFED | Static | Tomorrow — see you on campus. | Plan your day |  |  | https://example.rmit.local/open-day/plan |  | Comms | 1x1 ¦ 9x16 |  | 2026-09-07 | 2026-09-10 | 2026-09-12 | 2026-09-13